Smart Barrier

Remaining work: enclosure and cellular connectivity

ParkFNB arch-lock prototype

17 September 2026

Presentation: 22 September 2026

# 1. Where the barrier stands today

The prototype works. A lead-screw drive raises and lowers a curved arch over the parking bay. An MPU6050 reports the arch angle, the ESP32 drives the motor over PWM with a soft start and stop, and stall detection stops the motor if something blocks the arch. It connects over WiFi and takes commands over MQTT.

An arch design suits tight urban bays better than a boom barrier: the arch comes down over the vehicle rather than swinging sideways, so it needs no clearance beside the bay.

## What is already proven

| Part | State |
| --- | --- |
| Mechanism | Works — lead screw, rails, arch travel |
| Angle sensing | Works — MPU6050 with smoothing filter |
| Motor control | Works — PWM, soft start/stop, stall detect |
| Network | Works — WiFi + MQTT, takes remote commands |
| Replay protection | Works — incrementing command counter |
| Backend link | Works — app unlock and ANPR unlock both reach it |
| Enclosure | Open wooden base, exposed wiring |
| Cellular | Not started — WiFi only |

Two pieces of work remain, and they are not equally urgent. The enclosure is needed for the 22nd. Cellular is not — and attempting it this week would put the working barrier at risk.

# 2. Enclosure — making it presentable

Scope: appearance only. Weatherproofing is a production concern and is explicitly out of scope. The mechanism must not be touched — what works today must still work on the 22nd.

## What to build

| Item | What | Why it matters |
| --- | --- | --- |
| Electronics box | ESP32, motor driver and power supply inside a small ABS box | This is the most visibly untidy part today |
| Base skirt | 3-4 inch acrylic or foam-board skirt around the wooden base | Hides the rails and screw mess underneath |
| Arch finish | Reflective tape or paint over the foam pipe | Reads as traffic equipment rather than a craft project |
| Cable management | Spiral wrap and zip ties, one power lead out | A single loose wire makes the whole build look unfinished |
| Branding | ParkFNB logo sticker on the base | Thirty seconds of work; it starts looking like a product |

## Materials — roughly Rs. 600 to 900, all locally available

- Acrylic sheet 2-3 mm, or foam board, for the skirt

- Small ABS project box for the electronics

- Spiral cable wrap and zip ties

- Reflective tape, red and white, for the arch

- Double-sided tape and hot glue

- Matte spray paint, black or grey, for the base

## Sequence

### Day 5, evening — about 3 hours

- 1. Move the ESP32, driver and power into the box. Do not cut the motor or sensor wiring — route it out of the box instead

- 2. Test immediately after boxing — one full open and close cycle

- 3. Cut and fit the skirt on all four sides of the base

- 4. Apply reflective tape to the arch

### Day 6, morning — about 1 hour

- 5. Cable wrap and logo

- 6. Final test: five open and close cycles, then stop touching it

## Three things that commonly go wrong

- Wires work loose during boxing. This is why you test after every step rather than at the end. A single loose ground connection can take down the whole demo, and it is far harder to find once everything is assembled.

- The ESP32 overheats in a sealed box. Drill two or three ventilation holes.

- A metal box kills the WiFi antenna. Use ABS or another plastic. If only a metal box is available, mount the ESP32 outside it.

## Transport, the night before

- Detach the arch if it comes off cleanly; otherwise wrap it in bubble wrap

- Tape the screw and rails so nothing shifts in transit

- Carry a small toolkit: screwdriver, tape, spare jumper wires

- Bring the power supply and an extension cord — the venue socket may be far

- Record a video of the barrier working on Day 6 morning — the fallback if the hardware fails on stage

## On stage

Put the barrier on the table beside the laptop. The ANPR service reads a plate and the arch lifts. This is the moment the audience reaches for their phones.

If the hardware fails, start the device simulator and say: "the barrier is a device on the network — here is the same command going to the simulator." The architecture is identical, so the demo survives.

# 3. Cellular — moving from WiFi to a 4G SIM

Do not attempt this before 22 September. Demo on WiFi and put cellular on the roadmap slide.

## Why not now

| Step | Realistic time |
| --- | --- |
| Order the module, antenna and power parts; wait for delivery | 2-3 days |
| Wire it and debug the power rail | 1 day |
| TinyGSM, TLS and MQTT bring-up | 1-2 days |
| Total | 4-6 days |

The risk is not that cellular arrives late. The risk is that half-finished cellular work breaks a barrier that currently works.

## Why it matters commercially

| With WiFi only | With cellular |
| --- | --- |
| Needs the owner’s WiFi password | Works standalone, out of the box |
| Breaks when the router is replaced | Independent of the site network |
| Limited to the building’s range | Open lots, street parking, remote plots |
| Homes and small buildings only | Any location |

Most parking worth monetising — open lots, street bays, vacant plots — has no WiFi at all. Cellular is what makes the addressable market real. About Rs. 1,900 per unit plus roughly Rs. 100 a month.

## Why the change is small

The MQTT library runs on any Arduino Client object, and WiFi appears in only six places in the firmware.

| Location | Today | Becomes |
| --- | --- | --- |
| Includes | WiFi.h, WiFiClientSecure.h | TinyGsmClient.h |
| Client object | WiFiClientSecure | TinyGsmClientSecure |
| Connect routine | ensureWifi() | ensureNetwork() |
| Telemetry | WiFi.RSSI() | modem.getSignalQuality() |
| Boot log | WiFi.localIP() | modem.getLocalIP() |
| Main loop | one call to ensureWifi() | one call to ensureNetwork() |

Everything else is untouched: motor control, angle sensing, stall detection, the replay counter, the MQTT topics, the backend, and all three apps.

// ---- before ----

WiFiClientSecure netClient;

PubSubClient     mqtt(netClient);

// ---- after ----

#define TINY_GSM_MODEM_A7672X

TinyGsm             modem(Serial1);

TinyGsmClientSecure netClient(modem);

PubSubClient        mqtt(netClient);

## Module choice

| Module | Network | Cost | Verdict |
| --- | --- | --- | --- |
| SIM800L | 2G only | Rs. 200-300 | Do not buy — 2G is being shut down in India |
| A7672S | 4G Cat-1 | Rs. 1,200-1,600 | Recommended — datasheet already in the repo |
| SIM7600 | 4G Cat-4 | Rs. 1,800-2,500 | Also fine, better documented, costs more |
| SIM7670 | 4G Cat-1 | Rs. 1,500-2,000 | Compact alternative |

A barrier command is around 100 bytes, so Cat-1 bandwidth is far more than enough.

## Bill of materials

| Item | Spec | Cost |
| --- | --- | --- |
| A7672S module | Breakout board with SIM slot | Rs. 1,400 |
| LTE antenna | u.FL / IPEX pigtail | Rs. 150 |
| Buck converter | 5V to 4.0V, rated 3A | Rs. 120 |
| Bulk capacitor | 1000uF low-ESR, next to the module | Rs. 20 |
| Power supply | 5V 3A — the current one is likely not enough | Rs. 250 |
| IoT M2M SIM | Not a consumer SIM | Rs. 50-100/month |
| Total hardware |  | about Rs. 1,900 |

## The two traps

### Power — this is the one that catches people

A 4G module draws up to 2A in transmit bursts. The ESP32 regulator cannot supply that. Powered from the ESP32 pins, the module will brown out and reboot at random — usually just as it tries to connect, which looks exactly like a firmware or network bug.

5V 3A supply

|

+--> buck 4.0V --+--> A7672S VBAT

|                |

|             1000uF   <- as close to the module as possible

|

+--> ESP32 5V in

Ground must be common across all three.

Budget a full day for power debugging. Most failed cellular builds fail here, not in software.

### The SIM and the APN

- Use an IoT or M2M SIM, not a consumer one. Consumer plans drop idle data sessions.

- Expected usage is 5-10 MB a month — MQTT keepalives plus commands. The cheapest M2M plan is ample.

- The APN string must match the carrier exactly. A wrong APN is indistinguishable from no signal.

## Other things to get right

- Timeouts change scale. WiFi connects in about 2 seconds; cellular registration takes 10-60 seconds on first boot. Raise the timeout, and never block the main loop waiting — the motor control tick must keep running.

- Keepalive. Currently 30 seconds. On cellular, raise it to 60-120: fewer wakeups, less data, and carrier NAT still holds the session.

- TLS improves. The A7672S terminates TLS in the modem, so the insecure-certificate shortcut in the current firmware disappears. Worth a line on the architecture slide.

- Add a watchdog. Cellular modems do lock up. Power-cycle the module after N failed connection attempts.

Keep both transports behind a build flag. The WiFi build must still compile and run — that is the fallback whenever a demo is coming up.

## Plan, after the presentation

| Day | Work | Time |
| --- | --- | --- |
| 1 | Order the parts — shipping is the long pole | 30 min |
| 2 | While waiting: refactor to ensureNetwork(), add the build flag, confirm the WiFi build still works | 3-4 hr |
| 3 | Parts arrive. Wire the power, confirm the module answers AT commands | 3-4 hr |
| 4 | TinyGSM: register on the network, open a data session, connect MQTT | 4-6 hr |
| 5 | End to end: open and close from the app over 4G. Measure latency | 3 hr |
| 6 | Soak test: 24 hours connected, count reconnects and data used | 1 day |

Order the parts this week even though the work starts after the 22nd. Shipping is the only part you cannot compress.

## Acceptance criteria

- The barrier opens from the consumer app over 4G, with no WiFi present

- Command latency under 3 seconds end to end

- Survives 24 hours connected with fewer than 5 reconnects

- Uses under 10 MB in 24 hours

- Recovers on its own after the module is power-cycled

- The WiFi build still compiles and runs from the same source

# 4. Summary

| Work | When | Effort |
| --- | --- | --- |
| Enclosure and finishing | Day 5 evening + Day 6 morning | 4 hours |
| Record a backup video | Day 6 morning | 30 min |
| Order 4G parts | This week | 30 min |
| Cellular build | After 22 September | 5-6 days |

## What to say on stage

"Today it runs on WiFi. Production units ship with 4G, because real parking lots do not have WiFi. The transport layer is already abstracted — it is a client-object swap, not a rewrite."

That sentence shows the thinking without taking on the risk. It reads as a strength, not an excuse.

The barrier already does the one thing that matters: it refuses to open when the booking is not paid. Everything in this document is finishing, not building.