Cellular Barrier

Moving the ESP32 barrier from WiFi to a 4G SIM

ParkFNB  ·  16 September 2026

# 1. The decision first

Do NOT attempt this before 22 September. Demo on WiFi, put cellular on the roadmap slide.

The reasoning, plainly:

| Step | Realistic time |
| --- | --- |
| Order module + antenna + power parts, wait for delivery | 2-3 days |
| Wire it, debug the power rail | 1 day |
| TinyGSM + TLS + MQTT bring-up and debugging | 1-2 days |
| Total | 4-6 days |

You have 6 days, and they are already committed to ANPR, the seed script and rehearsal. The real risk is not that cellular fails to arrive — it is that half-finished cellular work breaks the barrier demo that already works.

## What to say on stage instead

"Today it runs on WiFi. Production units ship with 4G, because real parking lots do not have WiFi. The firmware’s transport layer is already abstracted — it is a client-object swap, not a rewrite."

This shows you have thought it through, without taking on the risk. It is a strength, not an excuse.

# 2. Why the swap is genuinely small

The firmware is already structured for this. PubSubClient runs on top of any Arduino Client object, and WiFi only appears in a handful of places in parkbnb_esp32.ino.

| Location | What it does | Change needed |
| --- | --- | --- |
| line 13-14 | WiFi.h / WiFiClientSecure.h includes | Replace with TinyGSM |
| line 30 | WiFiClientSecure netClient | TinyGsmClientSecure |
| ensureWifi() | Connect + 15s timeout + LED blink | Rewrite as ensureNetwork() |
| line 147 | WiFi.RSSI() in telemetry | modem.getSignalQuality() |
| line 325 | WiFi.localIP() in the boot log | modem.getLocalIP() |
| loop() | Calls ensureWifi() once | Calls ensureNetwork() |

Everything else is untouched: motor control, MPU6050 angle sensing, stall detection, the replay counter, MQTT topics, the backend, and all three apps.

## The core change, in full

// ---- before ----

#include <WiFi.h>

#include <WiFiClientSecure.h>

WiFiClientSecure netClient;

PubSubClient     mqtt(netClient);

// ---- after ----

#define TINY_GSM_MODEM_A7672X

#include <TinyGsmClient.h>

TinyGsm             modem(Serial1);

TinyGsmClientSecure netClient(modem);

PubSubClient        mqtt(netClient);

And ensureWifi() becomes:

void ensureNetwork() {

if (modem.isGprsConnected()) return;

modem.restart();

if (!modem.waitForNetwork(60000L)) return;   // tower registration

modem.gprsConnect(APN, APN_USER, APN_PASS);  // data session

}

# 3. Hardware — what to buy

## Module choice

| Module | Network | Approx cost | Verdict |
| --- | --- | --- | --- |
| SIM800L | 2G only | ₹200-300 | Do not buy — 2G is being shut down in India |
| A7672S | 4G Cat-1 | ₹1200-1600 | Recommended — you already have the datasheet |
| SIM7600 | 4G Cat-4 | ₹1800-2500 | Also fine, better documented, costs more |
| SIM7670 | 4G Cat-1 | ₹1500-2000 | Compact alternative |

A7672S is the right pick. A barrier command is roughly 100 bytes — Cat-1 bandwidth is far more than enough, and the datasheet is already in docs/research/A7672S.pdf.

## Bill of materials

| Item | Spec | Approx cost |
| --- | --- | --- |
| A7672S module | On a breakout board with a SIM slot | ₹1400 |
| LTE antenna | u.FL / IPEX pigtail | ₹150 |
| Buck converter | 5V → 4.0V, 3A rated | ₹120 |
| Bulk capacitor | 1000µF electrolytic, low ESR | ₹20 |
| IoT M2M SIM | Jio / Airtel M2M plan | ₹50-100 / month |
| Power supply | 5V 3A (existing supply may not be enough) | ₹250 |
| Total hardware |  | ≈ ₹1900 |

# 4. The two things that actually go wrong

## Trap 1 — power (this is the big one)

A 4G module draws up to 2A in transmit bursts. The ESP32’s onboard 3.3V regulator cannot supply that. If you power the module from the ESP32 pins, it will brown out and reboot at random — usually right when it tries to connect, which makes it look like a firmware or network bug.

5V 3A supply

│

├──▶ buck 4.0V ──┬──▶ A7672S VBAT

│                │

│            1000µF  ← as close to the module as possible

│

└──▶ ESP32 5V in

GND must be common across all three.

Budget a full day for power debugging. Nearly every failed cellular build fails here, not in software.

## Trap 2 — the SIM and the APN

- Use an IoT / M2M SIM, not a consumer SIM. Consumer plans can drop idle data sessions and are billed for far more data than a barrier will ever use.

- Expected usage is 5-10 MB/month — MQTT keepalives plus commands. The cheapest M2M plan is ample.

- The APN string must match the carrier exactly (Jio: jionet, Airtel: airtelgprs.com). A wrong APN looks exactly like no signal.

# 5. Firmware changes in detail

## config.h — new entries

// ---------- Cellular ----------

#define APN             "jionet"      // carrier APN

#define APN_USER        ""

#define APN_PASS        ""

#define SIM_PIN         ""            // usually blank

#define PIN_MODEM_TX    27            // ESP32 TX -> module RX

#define PIN_MODEM_RX    14            // ESP32 RX -> module TX

#define PIN_MODEM_PWRKEY 4            // power-on pulse

#define NET_MODE_CELLULAR 1           // 0 = WiFi, 1 = cellular

Keep both paths behind NET_MODE_CELLULAR. The WiFi build must still compile and run — that is your fallback when a demo is coming up.

## Things to get right

- Timeouts change scale. WiFi connects in ~2s; cellular registration takes 10-60s on first boot. Raise the connect timeout and never block loop() waiting for it — the motor control tick must keep running.

- Keepalive. Currently 30s. On cellular, raise it to 60-120s: fewer wakeups, less data, and carrier NAT still holds the session.

- Signal in telemetry. Replace WiFi.RSSI() with modem.getSignalQuality() (0-31 scale). The Device model already stores rssi, so nothing changes in the backend or the admin panel.

- TLS. The A7672S does TLS in the modem, so setInsecure() disappears. This is a security improvement, worth one line on the architecture slide.

- Watchdog. Cellular modems do lock up. Add a hardware watchdog that power-cycles the module via PWRKEY after N failed connection attempts.

# 6. Post-presentation plan

| Stage | Work | Time |
| --- | --- | --- |
| Day 1 | Order parts (order first — shipping is the long pole) | 30 min |
| Day 2 | While waiting: refactor into ensureNetwork(), add NET_MODE flag, verify the WiFi build still works | 3-4 hr |
| Day 3 | Parts arrive. Wire power, confirm the module boots and responds to AT commands over serial | 3-4 hr |
| Day 4 | TinyGSM: register on the network, open a data session, connect MQTT | 4-6 hr |
| Day 5 | End-to-end: open/close from the app over cellular. Measure command latency | 3 hr |
| Day 6 | Soak test — 24 hours connected, count reconnects and data used | 1 day |

Order the parts now, even though the work starts after the 22nd. Shipping is the only thing you cannot compress.

## Acceptance criteria

- Barrier opens from the consumer app over 4G, with no WiFi present

- Command latency under 3 seconds end to end

- Survives 24 hours connected with fewer than 5 reconnects

- Data usage under 10 MB over 24 hours

- Recovers on its own after the module is power-cycled

- The WiFi build still compiles and runs from the same source

# 7. Why this matters commercially

This is worth one line on the roadmap slide, because it changes who you can sell to:

| With WiFi only | With cellular |
| --- | --- |
| Needs the owner’s WiFi password | Works standalone, out of the box |
| Breaks when the router is replaced | Independent of the site’s network |
| Range limited to the building | Open lots, street parking, remote plots |
| Owner’s network is a support burden | You control the whole link |
| Homes and small buildings only | Any location |

Most parking that is worth monetising — open lots, street bays, vacant plots — has no WiFi at all. Cellular is not a nice-to-have; it is what makes the addressable market real. Roughly ₹1,900 per unit plus ₹100 a month.

Bottom line: order the parts this week, build it after the 22nd, demo on WiFi and say the sentence.